## Start Here
Bathroom Remodel Budget & Project Planner
From Bath Calculator (bathcalculator.com) · 2027 pricing
How to use this planner
1. Estimate | Choose your options in the yellow cells. The estimate uses the same cost model as the calculator on bathcalculator.com.
2. Budget Tracker | Set your budget, then log quotes and actual spending by category. Variances update automatically.
3. Bids | Compare up to three contractor bids side by side before you sign.
4. Timeline | Plan each phase of the project. Dates roll forward from your start date.
5. Payments & Financing | Map out the payment schedule and compare ways to pay, with monthly payments calculated for you.
6. Shopping List | Track materials and fixtures, order dates, and delivery status, with links to shop.
Color key
Yellow cell, blue text | Inputs: change these.
Black text | Formulas: calculated for you. Avoid typing over them.
Green text | Pulled from another tab.
Free cost calculators
Bathroom remodel cost
Small bathroom remodel
Walk-in shower
Bathtub replacement
Vanity installation
Tile calculator
Bathroom flooring
Costs by state
All calculators
Ready for quotes?
Get quotes from local remodelers
Find bathroom remodelers on Thumbtack
Estimates are national average planning figures, not quotes. Some links in this planner are affiliate links; Bath Calculator may earn a commission at no cost to you.

## Estimate
Remodel Cost Estimate
Same cost model as the bathcalculator.com homepage calculator. Change the yellow cells.
Your project | Choice | Calculation (before state index) | Amount
Your state | National average | State cost index | 1
Bathroom size (sq ft) | 40 | Prep, rough-in & finish labor | 4800
Project scope | Standard remodel | Demolition | 1520
Finish level | Midrange | Shower / tub | 2800
Shower / tub | Tub-shower combo | Flooring | 480
Flooring | Ceramic tile | Wall tile | 0
Heated floors | No | Vanity & countertop | 1500
Wall tile | None | Toilet | 550
Vanity | Stock vanity | Faucets & fixtures | 1500
Countertop | Cultured marble | Extras | 600
Toilet | Standard | Subtotal | 13750
New exhaust fan | Yes | Permits | 275
Lighting upgrade | No
New window | No
Accessibility features | No
Plumbing fixtures moved (#) | 0
Include permits | Yes
Doing labor yourself (DIY) | No
Example: a 5 × 8 hall bath (40 sq ft), standard midrange remodel, comes to about $14,000.
Estimated cost by category | Amount
Labor, prep & permits | 6595
Shower / tub | 2800
Flooring & wall tile | 480
Vanity & countertop | 1500
Toilet & fixtures | 2050
Fan, lighting & extras | 600
Typical total | 14025
Low estimate | 11921.25
High estimate | 16128.75
Contingency for surprises | 1402.5
Total budget with contingency | 15427.5
Cost per sq ft | 350.625
Contingency is 10% for cosmetic and standard remodels and 15% for full gut remodels, for problems found behind walls and floors.
Try the interactive calculator online
Get quotes from local remodelers

## Budget Tracker
Budget Tracker
Set your budget, then log each quote and payment in the detail table on the right. Category totals update automatically.
Your total budget | 15400
Cash available | 10000
Amount to finance | 5400
Line items: one row per quote, purchase, or payment
Category | Estimate | Quoted | Spent | Remaining | Variance vs estimate | Date | Item or vendor | Category | Quoted | Paid | Balance due | Notes
Labor, prep & permits | 6595 | 6500 | 1300 | 5295 | -95 | 2027-03-01 | Contractor deposit | Labor, prep & permits | 6500 | 1300 | 5200 | 10% deposit at signing
Shower / tub | 2800 | 0 | 0 | 2800 | 0 | 2027-03-04 | Vanity and top | Vanity & countertop | 1550 | 1550 | 0 | Ordered online
Flooring & wall tile | 480 | 300 | 300 | 180 | -180 | 2027-03-08 | Floor tile, 44 sq ft | Flooring & wall tile | 300 | 300 | 0 | Includes 10% overage
Vanity & countertop | 1500 | 1550 | 1550 | 0 | 50
Toilet & fixtures | 2050 | 0 | 0 | 2050 | 0
Fan, lighting & extras | 600 | 0 | 0 | 600 | 0
Contingency | 1402.5 | 0 | 0 | 1402.5 | 0
Total | 15427.5 | 8350 | 3150 | 12327.5 | -225
Budget left after spending | 12250
Percent of budget spent | 20.45%
Red variances mean a category is running over its estimate.
Rows 9 to 11 are examples. Replace them with your own entries.
Note on C4: Starts at the Estimate tab total plus contingency. Type over it with your own budget if you like.

## Bids
Compare Contractor Bids
Get at least three written bids for the same scope. Fill in each column, then compare.
| Contractor A | Contractor B | Contractor C
Company name | Example Remodeling Co.
Contact and phone
Total bid price | 15200
Your estimate (from Estimate tab) | 14025 | 14025 | 14025
Difference vs estimate | 1175
Includes demolition and haul-away? | Yes
Includes permits and inspections? | Yes
Includes materials and fixtures? | No
Allowances listed (tile, fixtures)?
Start date
Estimated duration (weeks)
Deposit required
Payment schedule | 10% at signing, then by milestone
Warranty on labor
License number verified?
Proof of insurance received?
References checked?
Online reviews (rating)
Gut feeling (1 to 5)
Notes
Red flags: large upfront deposits, cash-only payment, no written contract, pressure to sign today, or a bid far below the others.
Get quotes from local remodelers
Find bathroom remodelers on Thumbtack
How to choose a remodeling contractor

## Timeline
Project Timeline
Enter your start date. Each phase starts when the previous one ends; adjust the days to fit your project.
Project start | 2027-03-01
Phase | Task | Start | Days | End | Status | Notes
Plan | Set budget and wish list | 2027-03-01 | 5 | 2027-03-06 | Not started
Plan | Measure and choose layout | 2027-03-06 | 5 | 2027-03-11 | Not started
Plan | Get 3 bids and check references | 2027-03-11 | 14 | 2027-03-25 | Not started
Plan | Sign contract and pay deposit | 2027-03-25 | 3 | 2027-03-28 | Not started
Prepare | Apply for permits | 2027-03-28 | 10 | 2027-04-07 | Not started
Prepare | Order vanity, fixtures, tile, and door | 2027-04-07 | 14 | 2027-04-21 | Not started
Build | Demolition and haul-away | 2027-04-21 | 2 | 2027-04-23 | Not started
Build | Rough plumbing and electrical | 2027-04-23 | 4 | 2027-04-27 | Not started
Build | Rough-in inspection | 2027-04-27 | 2 | 2027-04-29 | Not started
Build | Drywall, cement board, and waterproofing | 2027-04-29 | 4 | 2027-05-03 | Not started
Build | Tile floor and shower walls | 2027-05-03 | 5 | 2027-05-08 | Not started
Build | Paint | 2027-05-08 | 2 | 2027-05-10 | Not started
Build | Install vanity, toilet, and fixtures | 2027-05-10 | 2 | 2027-05-12 | Not started
Build | Install shower door, mirror, and accessories | 2027-05-12 | 2 | 2027-05-14 | Not started
Finish | Final inspection | 2027-05-14 | 2 | 2027-05-16 | Not started
Finish | Punch list and final payment | 2027-05-16 | 3 | 2027-05-19 | Not started
| Estimated completion |  |  | 2027-05-19
| Total days |  |  | 79
| Tasks done |  |  | 0%
Order special-order items early: vanities, custom glass, and tile can take 2 to 8 weeks to arrive.
Formulas:
Start = [End, row above]
End = [Start]+[Days]

## Payments & Financing
Payments & Financing
Plan when payments are due and compare ways to pay for the project.
Contract price | 14025
Payment milestone | % of contract | Amount | Due date | Paid? | Amount paid
Deposit at signing | 10% | 1402.5 |  | No | 0
After demolition | 25% | 3506.25 |  | No | 0
After rough-in inspection | 25% | 3506.25 |  | No | 0
After tile is complete | 25% | 3506.25 |  | No | 0
Final payment after punch list | 15% | 2103.75 |  | No | 0
Total | 100% | 14025 |  |  | 0
Percentages should add up to 100%. Some states limit deposits on home improvement contracts, so check local rules.
Balance still owed |  | 14025
Compare financing options
Amount to finance | 5400
Option | Interest rate (APR) | Term (months) | Monthly payment | Total interest
Personal loan | 12% | 60 | 120.12 | 1807.201
Home equity line of credit (HELOC) | 8.5% | 120 | 66.9523 | 2634.2726
0% intro credit card (if paid off in time) | 0% | 18 | 300 | 0
Contractor or dealer financing | 9.99% | 84 | 89.6185 | 2127.9536
Rates are examples only. Enter the rates and terms you are actually offered. Intro 0% offers usually charge high interest on any balance left when the promotion ends.
Note on C4: Starts at your estimate. Replace it with your signed contract price.

## Shopping List
Materials & Fixtures Shopping List
Starter list with typical midrange prices. Edit quantities and prices to match what you choose.
Item | Category | Qty | Unit price | Total | Where to shop | Order by | Status
36-inch vanity | Vanity & countertop | 1 | 650 | 650 | Shop vanities at Lowe's |  | Need to order
Vanity top with sink | Vanity & countertop | 1 | 300 | 300 | Shop vanity tops at Lowe's |  | Need to order
Bathroom faucet | Toilet & fixtures | 1 | 150 | 150 | Shop faucets on Amazon |  | Need to order
Toilet | Toilet & fixtures | 1 | 300 | 300 | Shop toilets at Lowe's |  | Need to order
Shower valve and trim kit | Toilet & fixtures | 1 | 250 | 250 | Shop shower faucets at Lowe's |  | Need to order
Floor tile (sq ft, incl. 10% extra) | Flooring & wall tile | 44 | 4 | 176 | Shop tile at Lowe's |  | Need to order
Thinset, grout, and sealer | Flooring & wall tile | 1 | 120 | 120 | Shop setting materials at Lowe's |  | Need to order
Exhaust fan | Fan, lighting & extras | 1 | 150 | 150 | Shop exhaust fans at Lowe's |  | Need to order
Vanity light | Fan, lighting & extras | 1 | 150 | 150 | Shop vanity lights at Lowe's |  | Need to order
Mirror or medicine cabinet | Fan, lighting & extras | 1 | 150 | 150 | Shop mirrors at Lowe's |  | Need to order
Shower door | Shower / tub | 1 | 500 | 500 | Shop shower doors at Lowe's |  | Need to order
Grab bars | Fan, lighting & extras | 2 | 40 | 80 | Shop grab bars at Lowe's |  | Need to order
Towel bars and accessories | Fan, lighting & extras | 1 | 100 | 100 | Shop bath hardware at Lowe's |  | Need to order
Paint (gallons) | Labor, prep & permits | 2 | 45 | 90 | Shop paint at Lowe's |  | Need to order
Total materials |  |  |  | 3166
Shopping links are affiliate links: Bath Calculator may earn a commission at no extra cost to you. Prices are typical midrange examples, not quotes.

## Lists
Lookup tables
Cost model values from the Bath Calculator homepage calculator (2027 pricing). Edit only if you want to change the model.
Scope
Scope | Base fixed $ | Base $/sq ft | Demo fixed $ | Demo $/sq ft | Contingency
Cosmetic refresh | 1500 | 15 | 400 | 0 | 10%
Standard remodel | 3000 | 45 | 1200 | 8 | 10%
Full gut remodel | 5000 | 70 | 2000 | 12 | 15%
Finish
Finish level | Multiplier | Wall tile $/sq ft | Fixtures $
Budget | 0.8 | 18 | 600
Midrange | 1 | 25 | 1500
High-end | 1.5 | 40 | 4000
ShowerTub
Shower / tub | Base cost $
None (half bath) | 0
Tub-shower combo | 2800
Prefab walk-in shower | 3500
Custom tiled shower | 7500
Tub plus separate shower | 11000
Freestanding tub plus shower | 15000
Floor
Flooring | $ per sq ft
Luxury vinyl plank | 7
Ceramic tile | 12
Porcelain tile | 16
Natural stone | 28
Walls
Wall tile | Area factor
None | 0
Wainscot | 1
Full height | 2.5
Vanity
Vanity | Cost $ | Tops
Pedestal sink | 600 | 0
Stock vanity | 1200 | 1
Semi-custom vanity | 2200 | 1
Double vanity | 3800 | 2
Custom vanity | 7000 | 2
Top
Countertop | Cost $ per top
Laminate | 0
Cultured marble | 300
Quartz | 900
Granite | 800
Marble | 1500
Toilet
Toilet | Cost $
Keep existing | 0
Standard | 550
Comfort height | 750
Smart toilet | 2200
Constants
Constant | Value
Heated floor $ per sq ft | 20
Heated floor thermostat $ | 400
Exhaust fan $ | 600
Lighting upgrade $ | 1500
New window $ | 1200
Accessibility package $ | 800
Per plumbing fixture moved $ | 2500
Permit rate | 2%
Permit minimum $ | 250
Permit maximum $ | 2000
DIY base labor factor | 0.85
Range spread (+/-) | 15%
States
State | Cost index
National average | 1
Alabama | 0.88
Alaska | 1.25
Arizona | 0.97
Arkansas | 0.87
California | 1.25
Colorado | 1.05
Connecticut | 1.15
Delaware | 1.03
District of Columbia | 1.2
Florida | 0.97
Georgia | 0.93
Hawaii | 1.3
Idaho | 0.96
Illinois | 1.05
Indiana | 0.93
Iowa | 0.95
Kansas | 0.92
Kentucky | 0.9
Louisiana | 0.9
Maine | 1
Maryland | 1.08
Massachusetts | 1.2
Michigan | 0.98
Minnesota | 1.03
Mississippi | 0.86
Missouri | 0.93
Montana | 0.96
Nebraska | 0.94
Nevada | 1.03
New Hampshire | 1.05
New Jersey | 1.18
New Mexico | 0.92
New York | 1.22
North Carolina | 0.92
North Dakota | 0.95
Ohio | 0.94
Oklahoma | 0.88
Oregon | 1.08
Pennsylvania | 1.02
Rhode Island | 1.1
South Carolina | 0.9
South Dakota | 0.9
Tennessee | 0.91
Texas | 0.93
Utah | 0.98
Vermont | 1.02
Virginia | 1
Washington | 1.15
West Virginia | 0.88
Wisconsin | 0.98
Wyoming | 0.95
YesNo
Yes / No
Yes
No
Status
Status
Not started
In progress
Done
On hold
Categories
Budget category
Labor, prep & permits
Shower / tub
Flooring & wall tile
Vanity & countertop
Toilet & fixtures
Fan, lighting & extras
Contingency